## Subtask Questions
Milestone # | Milestone Name | Task # | Task Name | New task name | Responsibility | Subtask # |  | Subtask Name | Multi-Question Form? | Question # | Question Text | Input Type
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 1 | Core business domain | text
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 2 | Industry vertical | text
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 3 | Key business processes | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 4 | Number of locations | number
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 5 | Key stakeholders | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 6 | Business goals & KPIs | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 7 | Current challenges | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 8 | Expected outcome | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 9 | Session reference | text
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 1 | Form | Understand client business operations | Yes | 10 | Additional notes | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 1 | Organisation hierarchy | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 2 | Decision-making structure | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 3 | Teams interacting with system | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 4 | Number of users | number
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 5 | Reporting lines | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 6 | Key contact per department | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 2 | Form | Understand organizational structure | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 1 | Current ERP/software | text
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 2 | Version/edition | text
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 3 | Modules actively used | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 4 | Integration points | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 5 | Known limitations | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 6 | Data export capability | yesno
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 7 | API availability | yesno
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 3 | Form | Understand existing software/application | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 1 | Pain point #1 | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 2 | Pain point #2 | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 3 | Pain point #3 | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 4 | Impact on operations | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 5 | Priority level | dropdown_hml
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 6 | Affected departments | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 4 | Form | Identify business pain points | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 1 | Expected outcome — automation | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 2 | Expected outcome — reporting | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 3 | Expected outcome — process | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 4 | Target go-live date | date
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 5 | Success criteria | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 6 | Regulatory requirements | long
1 | Initiation & Requirement | 1 | Business Understanding |  | Functional Consultant | 5 | Form | Understand expected business outcome | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 1 | Session date | date
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 2 | Session mode | dropdown_mode
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 3 | Attendees client | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 4 | Attendees team | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 5 | Topics covered | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 6 | MOM shared | yesno
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 7 | Follow-up actions | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 1 | Form | Conduct requirement gathering sessions | Yes | 8 | Next session date | date
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 1 | Report name | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 2 | Report frequency | dropdown_freq
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 3 | Source data | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 4 | Filters required | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 5 | Audience | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 6 | Output format | dropdown_fmt
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 7 | Priority | dropdown_hml
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 2 | Form | Capture report requirements | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 1 | Process name | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 2 | Current manual effort (hrs/day) | number
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 3 | Trigger condition | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 4 | Expected output | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 5 | Exceptions | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 6 | Approval needed | yesno
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 3 | Form | Capture process automation requirements | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 1 | Transaction type | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 2 | Number of approval levels | number
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 3 | Level 1 approver | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 4 | Level 2 approver | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 5 | Escalation logic | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 6 | Time limit (hours) | number
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 7 | Rejection handling | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 8 | Email trigger required | yesno
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 4 | Form | Capture approval workflow requirements | Yes | 9 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 1 | KPI name | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 2 | Calculation logic | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 3 | Data source | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 4 | Refresh frequency | dropdown_freq
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 5 | Target threshold | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 6 | Dashboard type | dropdown_dash
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 7 | Audience | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 5 | Form | Capture KPI and dashboard requirements | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 1 | BRD document version | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 2 | BRD prepared by | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 3 | BRD reviewed by | text
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 4 | BRD approval status | dropdown_rev
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 5 | BRD approval date | date
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 6 | Requirements count | number
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 7 | Open items | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 6 | Form | Document business requirements | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 1 | Mail trigger condition | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 2 | Mail recipients | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 3 | User access roles defined | yesno
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 4 | Access matrix attached | yesno
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 5 | Alert trigger condition | long
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 6 | Alert channel | dropdown_alert
1 | Initiation & Requirement | 2 | Business Requirement |  | Functional Consultant | 7 | Form | Document features list | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 1 | Process name | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 2 | Process owner | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 3 | AS-IS documented | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 4 | Flow diagram available | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 5 | Bottlenecks | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 6 | Number of manual steps | number
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 7 | Frequency | dropdown_freq
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 1 | Form | Analyze existing process flow | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 1 | Report name | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 2 | Generated by | dropdown_gen
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 3 | Frequency | dropdown_freq
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 4 | Key fields | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 5 | Accuracy issues | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 6 | Report audience | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 7 | Action needed | dropdown_action
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 2 | Form | Analyze current reports | Yes | 8 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 1 | Source system name | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 2 | Data available | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 3 | Export method | dropdown_export
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 4 | Data quality issues | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 5 | Data quality notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 6 | Access granted | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 3 | Form | Review source systems | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 1 | Master data entity | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 2 | Data source | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 3 | Completeness (%) | number
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 4 | Cleansing required | yesno
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 5 | Responsible team | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 4 | Form | Study available master data | Yes | 6 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 1 | Gap #1 | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 2 | Gap #2 | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 3 | Gap #3 | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 4 | Gap impact | dropdown_hml
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 5 | Recommended resolution | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 5 | Form | Identify gaps | Yes | 6 | Additional notes | long
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 1 | Activity name | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 2 | Department | text
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 3 | Frequency | dropdown_freq
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 4 | Time per execution (hrs) | number
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 5 | Automation feasibility | dropdown_yn_p
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 6 | Priority | dropdown_hml
1 | Initiation & Requirement | 3 | Initial Study |  | Functional Consultant | 6 | Form | Identify manual activities | Yes | 7 | Additional notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 1 | Report # | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 2 | Report name | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 3 | Source module | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 4 | Complexity | dropdown_hml
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 5 | Estimated effort (days) | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 6 | Priority | dropdown_hml
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 1 | Form | Define reports to be developed | Yes | 7 | Notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 1 | Dashboard name | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 2 | Key metrics | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 3 | Target audience | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 4 | Technology | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 5 | Estimated effort (days) | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 2 | Form | Define dashboards to be developed | Yes | 6 | Notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 3 | Form | Define automation scope | Yes | 1 | Automation name | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 3 | Form | Define automation scope | Yes | 2 | Type | dropdown_auto
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 3 | Form | Define automation scope | Yes | 3 | Estimated effort (days) | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 3 | Form | Define automation scope | Yes | 4 | Dependencies | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 3 | Form | Define automation scope | Yes | 5 | Notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 1 | Integration name | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 2 | Source system | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 3 | Target system | text
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 4 | Integration type | dropdown_int
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 5 | Frequency | dropdown_freq
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 6 | Estimated effort (days) | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 4 | Form | Define integrations required | Yes | 7 | Notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 1 | Exclusion #1 | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 2 | Exclusion #2 | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 3 | Exclusion #3 | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 4 | Reason | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 5 | Agreed with client | yesno
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 5 | Form | Define exclusions | Yes | 6 | Notes | long
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 1 | Total mandays | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 2 | Project start date | date
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 3 | Planned go-live date | date
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 4 | Buffer (days) | number
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 5 | Effort doc attached | yesno
1 | Initiation & Requirement | 4 | Scope Defining |  | Functional Consultant & Technical Team | 6 | Form | Estimate effort and timeline | Yes | 6 | Notes | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 1 | Internal review done | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 2 | Review date | date
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 3 | Reviewers | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 4 | Comments | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 5 | Final doc version | text
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 1 | Form | Review scope internally | Yes | 6 | Notes | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 1 | Client review date | date
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 2 | Client attendees | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 3 | Client feedback | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 4 | Changes requested | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 5 | Revised doc shared | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 2 | Form | Review scope with client | Yes | 6 | Notes | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 1 | Open point #1 | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 2 | Resolution #1 | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 3 | Open point #2 | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 4 | Resolution #2 | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 5 | All resolved | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 3 | Form | Clarify open points | Yes | 6 | Notes | long
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 1 | Scope freeze date | date
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 2 | Client acknowledged | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 3 | SPOC name | text
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 4 | SPOC sign-off | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 5 | Change control agreed | yesno
1 | Initiation & Requirement | 5 | Scope Finalization |  | Functional Consultant | 4 | Form | Freeze project scope | Yes | 6 | Notes | long
1 | Initiation & Requirement | 6 | Client Confirmation |  | Functional Consultant | 1 | Form | Present finalized scope | No | 1 | Present finalized scope | date
1 | Initiation & Requirement | 6 | Client Confirmation |  | Functional Consultant | 2 | Form | Obtain scope approval | No | 1 | Obtain scope approval | yesno
1 | Initiation & Requirement | 6 | Client Confirmation |  | Functional Consultant | 3 | Form | Obtain advance from client | No | 1 | Obtain advance from client | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 1 | PM name | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 2 | FC name | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 3 | Tech lead name | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 4 | Other members | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 5 | Client SPOC name | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 6 | Introduction completed | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 1 | Form | Introduce project team | Yes | 7 | Notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 1 | Scope doc version | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 2 | Key scope items | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 3 | Client queries | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 4 | Scope accepted | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 5 | Action items | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 2 | Form | Discuss project scope | Yes | 6 | Notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 1 | Project start date | date
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 2 | Go-live date | date
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 3 | Milestone timeline shared | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 4 | Client agreed | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 5 | Timeline doc attached | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 3 | Form | Discuss timelines | Yes | 6 | Notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 1 | Dependency #1 | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 2 | Owner #1 | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 3 | Dependency #2 | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 4 | Owner #2 | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 5 | Client dependencies | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 6 | Risk notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 4 | Form | Discuss dependencies | Yes | 7 | Notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 1 | Primary channel | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 2 | Meeting frequency | dropdown_freq
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 3 | Status report frequency | dropdown_freq
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 4 | Escalation matrix | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 5 | Client SPOC | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 6 | Team SPOC | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 7 | Comm plan shared | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 5 | Form | Finalize communication process | Yes | 8 | Notes | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 1 | Meeting date | date
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 2 | MOM prepared by | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 3 | MOM shared date | date
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 4 | MOM shared via | text
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 5 | Client acknowledged | yesno
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 6 | Action items | long
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 7 | Next meeting date | date
2 | Kick Off | 1 | Kick Off Meeting with Client |  | Functional Consultant | 6 | Form | Share MOM | Yes | 8 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 1 | Department name | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 2 | Discussion date | date
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 3 | Representative | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 4 | Topics discussed | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 5 | Pain points | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 6 | MOM shared | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 7 | Follow-up required | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 1 | Form | Conduct department-wise discussions | Yes | 8 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 1 | Process name | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 2 | Process owner | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 3 | Start trigger | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 4 | End condition | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 5 | Number of steps | number
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 6 | AS-IS diagram created | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 7 | Process frequency | dropdown_freq
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 8 | Pain points | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 2 | Form | Understand AS-IS process | Yes | 9 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 1 | Transaction name | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 2 | Originating module | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 3 | Transaction steps | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 4 | Data fields | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 5 | System validations | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 6 | Output/result | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 7 | Error handling | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 3 | Form | Capture transaction flow | Yes | 8 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 1 | Transaction requiring approval | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 2 | Approval level 1 | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 3 | Approval level 2 | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 4 | Approval level 3 | text
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 5 | Auto-approval conditions | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 6 | Rejection handling | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 7 | Notification trigger | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 8 | Time limit (hours) | number
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 4 | Form | Capture approval flow | Yes | 9 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 1 | Exception #1 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 2 | Handling #1 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 3 | Exception #2 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 4 | Handling #2 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 5 | Exception #3 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 6 | Handling #3 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 7 | All documented | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 5 | Form | Capture exception scenarios | Yes | 8 | Notes | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 1 | Rule #1 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 2 | Rule #1 trigger | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 3 | Rule #2 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 4 | Rule #2 trigger | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 5 | Rule #3 | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 6 | Rule #3 trigger | long
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 7 | Validated with client | yesno
3 | Process Study | 1 | Detailed Process Study |  | Functional Consultant | 6 | Form | Capture business rules | Yes | 8 | Notes | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 1 | Process name | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 2 | Tool used | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 3 | Diagram created | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 4 | Reviewed internally | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 5 | Shared with client | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 6 | Client feedback | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 7 | Diagram version | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 1 | Form | Prepare process flow diagrams | Yes | 8 | Notes | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 1 | Process name | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 2 | TO-BE owner | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 3 | Key changes from AS-IS | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 4 | TO-BE diagram created | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 5 | TO-BE steps | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 6 | Automation points | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 7 | Client approved | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 8 | Doc version | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 2 | Form | Document TO-BE process | Yes | 9 | Notes | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 1 | Module/area | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 2 | Total rules count | number
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 3 | Doc version | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 4 | Reviewed with client | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 5 | Exceptions noted | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 6 | Doc shared date | date
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 3 | Form | Document business rules | Yes | 7 | Notes | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 1 | Validation name | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 2 | Type | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 3 | Field name | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 4 | Validation logic | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 5 | Error message | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 6 | Reviewed by | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 7 | Approved | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 4 | Form | Document validations | Yes | 8 | Notes | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 1 | Report name | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 2 | Source data | text
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 3 | Filters/parameters | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 4 | Calculation logic | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 5 | Output columns | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 6 | Sorting/grouping | long
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 7 | Reviewed | yesno
3 | Process Study | 2 | Process Documentation |  | Functional Consultant | 5 | Form | Document report logic | Yes | 8 | Notes | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 1 | Walkthrough date | date
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 2 | Users attended | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 3 | Doc version | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 4 | Feedback received | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 5 | Revisions requested | number
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 6 | Revised version | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 7 | Sign-off obtained | yesno
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 1 | Form | Walkthrough documentation with users | Yes | 8 | Notes | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 1 | Comment #1 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 2 | Resolution #1 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 3 | Comment #2 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 4 | Resolution #2 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 5 | Comment #3 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 6 | Resolution #3 | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 7 | All resolved | yesno
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 2 | Form | Resolve comments | Yes | 8 | Notes | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 1 | Doc name updated | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 2 | Updated version | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 3 | Changes made | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 4 | Shared date | date
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 5 | Client acknowledged | yesno
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 3 | Form | Update process documents | Yes | 6 | Notes | long
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 1 | Sign-off doc name | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 2 | Sign-off date | date
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 3 | Signed by (client) | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 4 | Role of signatory | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 5 | Sign-off method | text
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 6 | Doc stored | yesno
3 | Process Study | 3 | Process Confirmation |  | Functional Consultant | 4 | Form | Obtain process sign-off | Yes | 7 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 1 | FRD doc name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 2 | FRD version | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 3 | FRD author | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 4 | FRD created date | date
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 5 | Total sections | number
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 6 | Internal review done | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 7 | Shared with tech team | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 1 | Form | Prepare FRD | Yes | 8 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 1 | Source #1 name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 2 | Source #1 system | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 3 | Source #1 format | dropdown_export
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 4 | Source #2 name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 5 | Source #2 system | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 6 | Source #3 name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 7 | All access confirmed | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 2 | Form | Define input sources | Yes | 8 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 1 | Output #1 name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 2 | Output #1 type | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 3 | Output #1 frequency | dropdown_freq
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 4 | Output #1 audience | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 5 | Output #2 name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 6 | Output #2 type | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 7 | Output format | dropdown_fmt
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 3 | Form | Define output requirements | Yes | 8 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 1 | Calculation name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 2 | Formula/logic | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 3 | Input fields | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 4 | Output field | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 5 | Edge cases | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 6 | Verified with client | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 4 | Form | Define calculations | Yes | 7 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 1 | Validation name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 2 | Field name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 3 | Validation rule | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 4 | Error message | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 5 | Type | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 6 | Approved | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 5 | Form | Define business validations | Yes | 7 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 1 | Report name | text
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 2 | Number of columns | number
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 3 | Column names | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 4 | Grouping/subtotals | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 5 | Header/footer | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 6 | Sample layout attached | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 7 | Layout approved | yesno
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 6 | Form | Define report layouts | Yes | 8 | Notes | long
4 | Requirement Specification | 1 | FRD to Technical Team |  | Functional Consultant | 7 | Form | Obtain FRD approval - Internal | No | 1 | Obtain FRD approval - Internal | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 1 | Architecture approach | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 2 | Technology stack | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 3 | Database platform | text
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 4 | Server environment | dropdown_deploy
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 5 | Third-party integrations | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 6 | Solution doc created | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 7 | Internal review done | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 1 | Form | Design technical solution | Yes | 8 | Notes | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 1 | Database platform | text
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 2 | Database name | text
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 3 | Schema design | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 4 | Key tables | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 5 | Indexing strategy | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 6 | Data archival approach | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 7 | DB design reviewed | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 2 | Form | Define database approach | Yes | 8 | Notes | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 1 | Data flow diagram created | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 2 | Source systems | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 3 | Transformation logic | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 4 | Target destination | text
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 5 | Real-time or batch | dropdown_auto
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 6 | Volume (records/day) | number
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 7 | Data flow reviewed | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 3 | Form | Define data flow | Yes | 8 | Notes | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 1 | Deployment environment | dropdown_deploy
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 2 | Deployment method | text
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 3 | CI/CD required | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 4 | Rollback plan | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 5 | Deployment checklist | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 4 | Form | Define deployment approach | Yes | 6 | Notes | long
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 1 | Total mandays | number
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 2 | Dev start date | date
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 3 | Planned completion | date
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 4 | Buffer (days) | number
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 5 | Resource allocation defined | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 6 | Plan shared | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 7 | Plan approved | yesno
4 | Requirement Specification | 2 | Plan, Approach, Architecture |  | Functional Consultant | 5 | Form | Finalize development plan (Timeline, Mandays) | Yes | 8 | Notes | long
5 | Development | 1 | Development | Database object creation | Technical Team | 1 |  | Database object creation | Yes | 1 | DB name | text
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 2 | Tables created | number
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 3 | Views created | number
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 4 | Stored procedures | number
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 5 | Indexes created | yesno
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 6 | DB script reviewed | yesno
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 7 | Deployed to dev | yesno
5 | Development | 1 | Development |  | Technical Team | 1 |  | Database object creation | Yes | 8 | Notes | long
5 | Development | 1 | Development | Data extraction development | Technical Team | 2 |  | Data extraction development | Yes | 1 | Data source | text
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 2 | Extraction method | dropdown_export
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 3 | Extraction frequency | dropdown_freq
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 4 | Fields extracted | long
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 5 | Transformation applied | long
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 6 | Error handling | yesno
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 7 | Extraction tested | yesno
5 | Development | 1 | Development |  | Technical Team | 2 |  | Data extraction development | Yes | 8 | Notes | long
5 | Development | 1 | Development | Business logic development | Technical Team | 3 |  | Business logic development | Yes | 1 | Module name | text
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 2 | Business logic | long
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 3 | Rules implemented | long
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 4 | Edge cases handled | long
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 5 | Unit tested | yesno
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 6 | Code reviewed | yesno
5 | Development | 1 | Development |  | Technical Team | 3 |  | Business logic development | Yes | 7 | Notes | long
5 | Development | 1 | Development | Report development | Technical Team | 4 |  | Report development | Yes | 1 | Report name | text
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 2 | Report type | text
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 3 | Data source/query | text
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 4 | Filters implemented | long
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 5 | Calculations verified | long
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 6 | Report format | dropdown_fmt
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 7 | Unit tested | yesno
5 | Development | 1 | Development |  | Technical Team | 4 |  | Report development | Yes | 8 | Notes | long
5 | Development | 1 | Development | Dashboard development | Technical Team | 5 |  | Dashboard development | Yes | 1 | Dashboard name | text
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 2 | Dashboard type | dropdown_dash
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 3 | KPIs displayed | long
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 4 | Refresh frequency | dropdown_freq
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 5 | Charts/visuals | long
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 6 | Mobile responsive | yesno
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 7 | Unit tested | yesno
5 | Development | 1 | Development |  | Technical Team | 5 |  | Dashboard development | Yes | 8 | Notes | long
5 | Development | 1 | Development | Validation implementation | Technical Team | 6 |  | Validation implementation | Yes | 1 | Validation name | text
5 | Development | 1 | Development |  | Technical Team | 6 |  | Validation implementation | Yes | 2 | Field/module | text
5 | Development | 1 | Development |  | Technical Team | 6 |  | Validation implementation | Yes | 3 | Validation rule | long
5 | Development | 1 | Development |  | Technical Team | 6 |  | Validation implementation | Yes | 4 | Error message | text
5 | Development | 1 | Development |  | Technical Team | 6 |  | Validation implementation | Yes | 5 | Test case passed | yesno
5 | Development | 1 | Development |  | Technical Team | 6 |  | Validation implementation | Yes | 6 | Notes | long
5 | Development | 1 | Development | Internal developer testing | Technical Team | 7 |  | Internal developer testing | Yes | 1 | Test date | date
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 2 | Modules tested | long
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 3 | Test cases executed | number
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 4 | Issues found | number
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 5 | Issues resolved | yesno
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 6 | Retest completed | yesno
5 | Development | 1 | Development |  | Technical Team | 7 |  | Internal developer testing | Yes | 7 | Notes | long
5 | Development | 1 | Development | Bug fixing | Technical Team | 8 |  | Bug fixing | Yes | 1 | Bug ID | text
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 2 | Bug description | long
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 3 | Severity | dropdown_sev
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 4 | Root cause | long
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 5 | Fix applied | long
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 6 | Fix tested | yesno
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 7 | Bug closed | yesno
5 | Development | 1 | Development |  | Technical Team | 8 |  | Bug fixing | Yes | 8 | Notes | long
6 | Internal Testing | 1 | Internal Testing | Prepare test scenarios | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 1 | Module name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 2 | Scenarios count | number
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 3 | Doc version | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 4 | Reviewed | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 5 | Edge cases included | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 6 | Negative scenarios | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 1 |  | Prepare test scenarios | Yes | 7 | Notes | long
6 | Internal Testing | 1 | Internal Testing | App testing | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 1 | Rule name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 2 | Test case | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 3 | Expected result | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 4 | Actual result | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 5 | Test result | dropdown_test
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 6 | Defect raised | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 7 | Defect ID | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 2 |  | Validate business rules | Yes | 8 | Notes | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 1 | Calculation name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 2 | Input values | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 3 | Expected output | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 4 | Actual output | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 5 | Variance | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 6 | Test result | dropdown_test
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 7 | Defect raised | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 3 |  | Validate calculations | Yes | 8 | Notes | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 1 | Report name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 2 | Test data | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 3 | Expected output | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 4 | Actual output | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 5 | Column count matched | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 6 | Accuracy verified | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 7 | Test result | dropdown_test
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 8 | Defect ID | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 4 |  | Validate report outputs | Yes | 9 | Notes | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 1 | Dashboard name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 2 | KPI name | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 3 | Expected value | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 4 | Actual value | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 5 | Variance | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 6 | Rendering correct | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 7 | Test result | dropdown_test
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 5 |  | Validate dashboard outputs | Yes | 8 | Notes | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 1 | Defect ID | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 2 | Defect title | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 3 | Module affected | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 4 | Severity | dropdown_sev
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 5 | Steps to reproduce | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 6 | Expected vs actual | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 7 | Assigned to | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 8 | Status | dropdown_closure
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 6 |  | Log defects | Yes | 9 | Notes | long
6 | Internal Testing | 1 | Internal Testing | Retest | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 1 | Defect ID retested | text
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 2 | Fix description | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 3 | Retest date | date
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 4 | Retest result | dropdown_test
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 5 | Defect closed | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 6 | Regression impact checked | yesno
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 7 |  | Retest fixes | Yes | 7 | Notes | long
6 | Internal Testing | 1 | Internal Testing |  | Technical Team & Functional Team | 8 |  | Internal testing sign-off | No | 1 | Internal testing sign-off | yesno
7 | Deployment for UAT | 1 | Deployment for UAT | Server Readiness | Technical Team | 1 |  | Server Readiness | No | 1 | Server Readiness | yesno
7 | Deployment for UAT | 1 | Deployment for UAT | Master data Deploy | Technical Team | 2 |  | Master data Deploy | No | 1 | Master data Deploy | yesno
7 | Deployment for UAT | 1 | Deployment for UAT | Deploy solution to UAT environment | Technical Team | 3 |  | Deploy solution to UAT environment | No | 1 | Deploy solution to UAT environment | date
7 | Deployment for UAT | 1 | Deployment for UAT | Load sample data | Technical Team | 4 |  | Load sample data | No | 1 | Load sample data | yesno
7 | Deployment for UAT | 1 | Deployment for UAT | Share UAT version | Technical Team | 5 |  | Share UAT version | No | 1 | Share UAT version | yesno
7 | Deployment for UAT | 2 | Post Deployment testing | Execute smoke testing | Technical Team | 1 |  | Execute smoke testing | No | 1 | Execute smoke testing | dropdown_pf
7 | Deployment for UAT | 2 | Post Deployment testing | Verify deployment | Technical Team | 2 |  | Verify deployment | No | 1 | Verify deployment | dropdown_pf
8 | UAT for End User | 1 | UAT for End User | Provide user training | Technical Team | 1 |  | Provide user training | No | 1 | Provide user training | yesno
8 | UAT for End User | 1 | UAT for End User | Conduct UAT walkthrough | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 1 | Walkthrough date | date
8 | UAT for End User | 1 | UAT for End User | End User testing | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 2 | Users attended | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 3 | Modules covered | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 4 | User queries | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 5 | Queries resolved | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 6 | Follow-up actions | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 7 | Walkthrough feedback | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 2 |  | Conduct UAT walkthrough | Yes | 8 | Notes | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 1 | Test case ID | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 2 | Description | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 3 | Tested by | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 4 | Test date | date
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 5 | Expected result | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 6 | Actual result | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 7 | Test result | dropdown_test
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 8 | Defect raised | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 3 |  | Execute user test cases | Yes | 9 | Notes | long
8 | UAT for End User | 1 | UAT for End User | Validate outputs | Technical Team | 4 |  | Validate outputs | Yes | 1 | Output name | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 2 | Validated by | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 3 | Validation date | date
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 4 | Matches expectation | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 5 | Issues noted | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 6 | Accepted by user | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 4 |  | Validate outputs | Yes | 7 | Notes | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 1 | Scenario name | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 2 | Description | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 3 | Data used | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 4 | Expected outcome | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 5 | Actual outcome | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 6 | Scenario passed | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 7 | Defect raised | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 5 |  | Validate business scenarios | Yes | 8 | Notes | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 1 | Observation ID | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 2 | Module | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 3 | Description | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 4 | Severity | dropdown_sev
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 5 | Raised by | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 6 | Status | dropdown_closure
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 7 | Resolution | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 6 |  | Log UAT observations | Yes | 8 | Notes | long
8 | UAT for End User | 1 | UAT for End User | Fix UAT defects | Technical Team | 7 |  | Fix UAT defects | Yes | 1 | Defect ID | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 2 | Description | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 3 | Fixed by | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 4 | Fix date | date
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 5 | Fix description | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 6 | Retest required | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 7 | Defect closed | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 7 |  | Fix UAT defects | Yes | 8 | Notes | long
8 | UAT for End User | 1 | UAT for End User | Re-deploy updated version | Technical Team | 8 |  | Re-deploy updated version | Yes | 1 | Version number | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 2 | Deployment date | date
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 3 | Environment | text
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 4 | Changes included | long
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 5 | Deployment verified | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 6 | Users notified | yesno
8 | UAT | 1 | UAT for End User |  | Technical Team | 8 |  | Re-deploy updated version | Yes | 7 | Notes | long
8 | UAT | 1 | UAT for End User | UAT sign-off | Technical Team | 9 |  | Obtain UAT sign-off | No | 1 | Obtain UAT sign-off | yesno
9 | Go Live | 1 | Go Live | Deploy production version | Technical Team | 1 |  | Deploy production version | Yes | 1 | Production date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 2 | Deployed version | text
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 3 | Deployed by | text
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 4 | Deployment method | text
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 5 | Downtime required | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 6 | Downtime duration (hrs) | number
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 7 | Deployment successful | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 1 |  | Deploy production version | Yes | 8 | Notes | long
9 | Go Live | 1 | Go Live | Configure production environment | Technical Team | 2 |  | Configure production environment | Yes | 1 | Server/env name | text
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 2 | Config checklist | long
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 3 | Database configured | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 4 | Connections configured | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 5 | SSL/security configured | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 6 | Config verified | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 2 |  | Configure production environment | Yes | 7 | Notes | long
9 | Go Live | 1 | Go Live | Validate production data | Technical Team | 3 |  | Validate production data | Yes | 1 | Validation date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 2 | Master data loaded | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 3 | Opening balances verified | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 4 | Historical data migrated | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 5 | Accuracy checked | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 6 | Data validation sign-off | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 3 |  | Validate production data | Yes | 7 | Notes | long
9 | Go Live | 1 | Go Live | Perform sanity testing | Technical Team | 4 |  | Perform sanity testing | Yes | 1 | Test date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 2 | Modules tested | long
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 3 | Test cases executed | number
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 4 | Test result | dropdown_pf
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 5 | Critical issues found | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 6 | Issues resolved | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 4 |  | Perform sanity testing | Yes | 7 | Notes | long
9 | Go Live | 1 | Go Live | Obtain go-live approval | Technical Team | 5 |  | Obtain go-live approval | Yes | 1 | Approval requested date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 2 | Approved by | text
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 3 | Approver designation | text
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 4 | Approval method | text
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 5 | Approval received | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 6 | Approval stored | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 5 |  | Obtain go-live approval | Yes | 7 | Notes | long
9 | Go Live | 1 | Go Live | Release to users | Technical Team | 6 |  | Release to users | Yes | 1 | Go-live date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 2 | Users notified | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 3 | Notification method | text
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 4 | User access configured | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 5 | Training refresher provided | yesno
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 6 | Hypercare start date | date
9 | Go Live | 1 | Go Live |  | Technical Team | 6 |  | Release to users | Yes | 7 | Notes | long
10 | Post Live Support | 1 | Post Live Support | Monitor application/report | Technical Team | 1 |  | Monitor application/report | Yes | 1 | Monitoring start date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 2 | Monitoring tool | text
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 3 | Monitoring frequency | dropdown_freq
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 4 | Performance metrics | long
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 5 | Alerts configured | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 6 | Issues identified | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 7 | Report shared | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 1 |  | Monitor application/report | Yes | 8 | Notes | long
10 | Post Live Support | 1 | Post Live Support | Resolve production issues | Technical Team | 2 |  | Resolve production issues | Yes | 1 | Issue ID | text
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 2 | Description | long
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 3 | Issue type | dropdown_support
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 4 | Priority | dropdown_priority
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 5 | Reported by | text
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 6 | Reported date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 7 | Resolution | long
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 8 | Resolved date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 9 | Closed | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 2 |  | Resolve production issues | Yes | 10 | Notes | long
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 1 | Query ID | text
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 2 | User name | text
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 3 | Query description | long
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 4 | Query type | dropdown_support
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 5 | Response provided | long
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 6 | Resolution date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 7 | User satisfied | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 3 |  | Resolve user queries | Yes | 8 | Notes | long
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 1 | Area of issue | text
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 2 | Baseline performance | text
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 3 | Optimization applied | long
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 4 | Improved performance | text
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 5 | Test result | dropdown_pf
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 6 | Changes deployed | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 4 |  | Fine tune performance | Yes | 7 | Notes | long
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 1 | Document name | text
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 2 | Document version | text
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 3 | Handed over to | text
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 4 | Handover date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 5 | Document type | text
10 | Support | 1 | Post Live Support |  | Technical Team | 5 |  | Handover project documents | Yes | 6 | Acknowledgement received | yesno
10 | Post Live Support | 1 | Post Live Support | Handover project documents | Technical Team | 5 |  | Handover project documents | Yes | 7 | Notes | long
10 | Post Live Support | 1 | Post Live Support | Project closure | Technical Team | 6 |  | Project closure | Yes | 1 | Closure date | date
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 2 | Closure report created | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 3 | Lessons learned documented | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 4 | Final sign-off obtained | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 5 | Signed by client | text
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 6 | Post-project review scheduled | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 7 | Project archived | yesno
10 | Support | 1 | Post Live Support |  | Technical Team | 6 |  | Project closure | Yes | 8 | Notes | long

## Summary
Milestone # | Milestone Name | Tasks | Subtasks | Total Questions
1 | Initiation & Requirement | 6 | 31 | 200
2 | Kick Off | 1 | 6 | 42
3 | Process Study | 3 | 15 | 119
4 | Requirement Specification | 2 | 12 | 85
5 | Development | 1 | 8 | 60
6 | Internal Testing | 1 | 8 | 57
7 | Deployment | 2 | 7 | 7
8 | UAT | 1 | 9 | 57
9 | Go Live | 1 | 6 | 43
10 | Support | 1 | 6 | 48